## First-Level Template_COWI (hidden)
[34 empty] | ACTIONPLANS | [21 empty] | 2020-02-14
Group | No | Correlation | [20 empty] | Correlation | [10 empty] | Jan | Feb | Mar | Apr | Maj | Jun | Jul | Aug | Sep | Okt | Nov | Dec | SIMU | SRJ | BATX | ANDZ | OSK | MENE | STD | MJSK | CHEE | PBSO | Status
General | G-1 | [7 empty] | 2 | [9 empty] | 2 |  |  | Integration CRUISE: 1) Combined Vision statement HX/CO 2) Preliminary implementation plan 3) Communication plan and procedures with COWI HR and communications and management workshop 4) Rollout of communication before/just around to official disclosure | [6 empty] | 2 | 2 |  |  |  | 1-3 | 1-3 | [10 empty] | A | C | C | C | I | I | I | I | I | R | 1) to be finalized with Hxgn 2) on track in the workstreams 3) done 4) after workshop BB
INDOLE | I-2 |  | 2 | [10 empty] | 2 |  |  | 1 |  |  | 2 |  | Define and design alternative lower cost product for CORYS 1) Conduct next level VSM for the most tiem consuming subprocesses 2) Low hangin fruits identification 3) Develop an action and implementation plans 4) Conduct a pilot 5) Evaluate results from pilot and identify adjustments to the plan 6) design final alternative production workflow |  |  |  | 1 | [5 empty] | 2 |  | 1 | 2-3 | 4 | 5-6 | [8 empty] | A: I; C: I; C: A; C: R | - need to be specific on the "low hanging fruits" and cost decrease potetnial; sales prices per km are today hundreds of Euros - the process needs to affect that visibly - present at next IB or TM
INDOLE | I-3 |  |  | 2 |  |  |  | 1 |  |  |  | 1 | 1 |  |  | 1 | [5 empty] | Develop and implement an AI based improvement for Orthophoto 1) Conduct next level VSM 2) Identify areas for improvements 3) Design AI architecture 4) Prepare the data for training 5) Conduct training and evaluate the results 6) Implement in production |  | 2 |  | 2 |  | 2 |  |  |  |  | 2 | 1-2 | 3-4 | 5 | 5 | 6 | [7 empty] | A: I; C: A; C: R; I: I; I: I | - on track
INDOLE | I-4 |  | 1 | 1 | 1 | 1 |  | 1 | [10 empty] | 2 |  |  | Develop a knowledge platform, including; revisiting and rewriting all process descriptions for projects and Sales, learning from exsiting projects 1) conduct a workshop with Sales and Projects for requirements evaluation 2) prepare the full and fianl list of requirements - DoD 3) chose the technical platform 4) Prepare the pilot area for testing the identified technical platform 5) Evaluation of the results via joint workshop with the sales and Projects 6) Revisit all the tender and projects processes and documentation 7) fill the system with the data 8) Go live in agile way 9) adjustments after a feedback | 1 | 2 |  | 1 |  | 1 | 2 |  |  |  | 1 | 1,3,6 | 2,3,4,6 | 3,4,6 | 5,6 | 6 | 6 | 7-8 | 8 | 9 |  |  |  | I | C | C | A | C |  |  | C |  |  | - on track - present at next IB/TM
Operations | O-5 |  |  |  |  | 2 |  | 1 | 1 |  | 2 |  |  |  | 1 |  | 1 |  | 2 |  |  | Redefine and simplify the PM procedures, combining the QMS, guidelines and financial system 1) Review PM procedures, QMS and compare with other industry leading procedures 2) Review financial system for projects together with controller 3) Implement Lean in PM, removal of all unnecessary processes. 4) Implement changes so all PMs also have a non-admin role in projects | 1 | 1 |  | 1 |  | 2 | 1 | 1 |  |  | 2 |  |  | 1-2 | 1-2 | 3-4 | 3-4 | [6 empty] | A: I; C: A; C: C; C: C; I: C | - next week meeting ANDZ, SRJ, OSK on improvements pbased on lean procedure - it was already agreed in 221 with SRJ to focus also on the processes outside CIL
Operations | O-6 | 1 | [5 empty] | 2 | [6 empty] | 1 |  | 2 |  |  |  |  | Use risk management to avoid write downs 1) Update handover procedures to have a higher focus on potential Risk and avoidance of the same 2) PFM’s to have a higher focus on Risk management in Sparring meetings 3) Monthly dialog with between VP and PFMs about Top 3 risk in projects and management of the same | 1 | 1 | 2 | 2 | 1 | 1 | 1 | 1 |  |  | 2 |  |  | 1 | 1 | 2-3 | 2-3 | [16 empty] | no update | bar: A to C; I to I
Operations | O-7 |  |  |  |  | 1 |  | 2 | [5 empty] | 1 | 1 |  | 2 |  |  |  |  | Improve the accuracy of estimates and calculation of costs 1) Further build on the databases started during September 2019, ensuring all is updated 2) Benchmark towards competitors in the industry to verify estimates are in the top 10% | 1 | 2 | 2 | 2 |  | 2 | 1 |  | 2 | 1 | 1 | 1-2 | 1-2 | [10 empty] | I | A | C | R | R |  |  |  | C |  | no update
Operations | O-8 |  | 2 | 2 | 2 | 2 |  | 2 |  |  | 2 | 1 | 1 |  |  |  | 2 |  | 1 |  | 1 | Roll out lean process in every service line 1) Increase the level of knowledge of lean in projects, by involvement and training 2) Promote lean to create an even more positive mindset 3) Plan and activate lean action plan 2020 | 1 | 2 | 1 | 2 |  | 2 | 1 |  |  |  | 2 | 1-2 | 1-2 | 1-2 | 1-3 | 1-3 | 1-3 | 1-3 | 1-3 | 1-3 | 1-3 | 1-3 | 1-3 | I | A | A | R | R |  |  | R | I |  | no update
Operations | O-9 | 2 | 1 | 1 | 1 | 1 |  | 1 | 1 | [5 empty] | 1 |  | 2 |  | 1 |  | 2 | Increase the dialogue about financial performance. 1) Define communication matrix about the needed financial dialog 2) Describe and implement common platform for reporting 3) Present regular financial updates as defined in 1) 4) Celebrate positive results, promote winners 5) Focus on the worst- and the best financial results | 1 | 1 | 1 | 2 | 1 | 2 | 2 | 1 |  |  | 2 | 1 | 1 | 2-3 | 2-3 | 4-5 | 4-5 | 4-5 | 4-5 | 4-5 | 4-5 | 4-5 | 4-5 | A | R | R | R | I | I | I | I | C | C | no update
Operations | O-10 |  | 1 | 1 | 1 | 1 |  | 2 |  |  | 1 | 1 | 1 |  | 1 |  | 1 |  | 2 |  | 1 | Introduce incentive for suggestions that result in efficiency improvements 1) Revise existing incentive schemes in Mapping operations, and adjust to include suggestions resulting in efficiency improvements 2) Implement new incentive systems globally and locally | 1 | 1 |  |  |  |  | 2 | 1 |  |  | 1 | 1 | 1 | 2 | 2 | [8 empty] | A: I; C: A; C: C; I: C; I: C | no update
Operations | O-19 | [5 empty] | 3 | [14 empty] | Specific set of actions related to aerial surveying cost (Planning, partnerships, own operation) 1) [Planning] Arrange meeting/training with Leica/Hexagon for knowledge sharing about flight planning and possible improvements 2) [Partnerships] Define a list of requirements to become preferred partner for Aerial Survey 3) [Partnerships] Set-up meetings with preferred partners to discuss future cooperation pricing mechanisms to make the cooperation work smoothly 4) [Partnerships] Create a set of guidelines for working with Aerial Survey partners 5) [Own operation] Review current set-up and prepare for a future for aircraft type 6) [Own operation] Arrange meeting with Leica/Hexagon about the future for sensors to ensure a match between Aircraft, sensors and projects 7) [Own operation] Discuss market needs with sales 8) [Own operation] Review and simplify the administrative work in Aerial Survey 9) [Own operation] Review, and if needed adjust, number of staff for future Aerial Survey set-up 10) [Own operation] Review operational guidelines and methods, example; travelling guidelines, on site processing in periods with bad weather etc. | [11 empty] | 1-2, 5-6 | 1-3, 7,10 | 1-3, 8 | 4, 8 | 9 | 9 | [6 empty] | I | A | I | C | C |  |  | C |  |  | no update
Sales | S-11 | 1 | [7 empty] | 2 |  |  | 2 |  |  | 1 |  | 2 |  | 1 |  | Product Support Group: 1) Identify Products , one brand(ing) including both HCP as ''COTS'' 2) Explain/describe COTS 3) Identify skillsets: backoffice and customer facing 4) Identify systems requirements: integration WMS service Denmark 5) describe workflow & structure & administrative processes 6) implementation | 1 |  |  | 2 | [6 empty] | 2 | 1-5 | 5 | 5 | [19 empty] | - on track; - document v2 shared - changes suggested in 221 with MENE - product development process to describe generically (ANDZ) then map to the Product Group / INDOLE | bar: A to C; I to I; I to R
Sales | S-12 | 1 | [5 empty] | 2 |  |  |  | 2 | 2 |  |  |  | 2 |  | 1 | 1 |  | EBIT Boost measures 1 Market intel by Sales a.o historic pricing 2 Subscription pricing roll out |  |  |  | 2 | [7 empty] | 1 | 1 | 1 | 1.2 | 1.2 | 1.2 | 1 | 1 | 1 | 1 | 1 | 1 | I | I | A | I | I | R | R |  |  |  | - on track
Sales | S-13 | 2 | [6 empty] | 1 |  |  | 2 | 1 | [8 empty] | New NMA focus 1 Identify the top 10 Ortho/Lidar/mapping/content programs (2020) in EU 2 Integrate in Hex current initiatives 3 Assign Responsibility ( Sales/Projects) 4 Proactive approach /influence requirements 5 Hire Local consultants and/or further dev Sales team | [8 empty] | 2 | 1 |  | 1 | 1.2 | 1.2 | 1.2 | 1.2 | 1.2 | 1.2 | 1.2 | 1.2 |  |  |  | A: I; C: A; I: R; I: R | - Germany is first - part of joit AP with Hexagon next week
Sales | S-14 | 1 | [5 empty] | 1 |  | 2 |  |  | 2 |  |  | 2 | 1 | 2 |  | 1 |  | Content Resales 1 Develop Indirect Sales channel EU Content 2 In depth Country plan for Top 5 Countries EU 3 Hire add Sales Direct/Channel Manager (e.g. France and Scan) 4 EU wide targetted marketing campaign/ Market campaign through lead generation company 5 Leverage lessons learnt Hex from US -> EU 6 Knowledge transfer from Hexagon (f.e. ideal sw for visiualisation etc...) |  |  |  | 2 | 1 |  | 1 |  |  |  | 2 | 1,2,3 | 1,2,3 | 1,2,3 | 1 | 1 | 1 | [6 empty] | A: C; C: A; I: R | *- part of joint AP with HxGN next week - how to increase channel partner base and incentivize them?
Sales | S-15 | 1 | 1 |  |  |  |  | 1 | [5 empty] | 2 | [7 empty] | CORYS 1 Concretise the forecast 2 Intensifie Follow up meetings 3 KAM assignment 4 Identify other markets/users light rail ( outside CORYS) 5 Educate Hexagon | [6 empty] | 1 |  |  | 2 | 1 | 1,2,3 | 1,2,3 | 1,2,3 | 2 | 2 | 2 | 2 | 2 | 2 | [13 empty] | *- on track | bar: A to C
Sales | S-16 | 1 | [5 empty] | 1 |  | 2 |  |  | 2 |  |  | 1 |  | 1 |  | 1 |  | HxGN content: Plan and execute Business dev into private accounts : Here, TomTom, Conti,… Identify indiv targets, action plan |  |  |  | 2 | [5 empty] | 2 | 2 | [12 empty] | A: I; C: A; I: R | - part of Hexagon AP next week
Sales | S-17 | 1 | [5 empty] | 1 |  | 1 |  | 2 |  |  | 2 | 1 |  | 1 |  | 1 |  | COTS Actions 1 COTS Sweden definition /launch 2 Relaunch DDO 2020 --> SOP 3 Knowledge tranfer between COWI & Hexagon 4 Connect with HCP Oblique program |  |  |  | 2 |  |  |  |  | 1 | 1 | 1 | 1.2 | 1.2 | 1.2 | 1.2 | 1.2 | 1.2 | [6 empty] | A: C; C: I; C: A; I: R | *- DDO 2020 possibly launched - other COTS subject to Contentprogram
INDOLE | I-18 | [8 empty] | 2 |  |  | 1 |  |  | 1 |  | 1 |  |  |  | Content end-to-end handling system: 1) Description of specifications (fron end for sales and channel partners) 2) Analysis of existing Hexagon systems (front and back end) 3) Gap Analysis 4) Implementation with Hx IT | 2 | [10 empty] | 1 | 2 | 3 | 4 | [8 empty] | A: I; C: A; C: R; I: R | - next week
Hoshin - Kanri Matrix BU4 Mapping |  | Turnover > 200 MDKK | Reduction of the CORYS cost by 35% compared to 2019 | Reduction of the orthophoto production cost by 50% compared to 2019 | Reduction of processing cost for Lidar by 50'% compared to 2019 | Reduce Projectmanagement cost by 20% compared to 2019 | Implement a workflow that allows always access to the most competitive flight cost in Europe | EBIT > 15% projects and >30% content | Successful integration into Hexagon | Competitive state-of-the-art order handling system for content | Implement Lean approach in every project in 2020 | Grow NMA business by 15% compared to 2019 buget | Increase content resales by 25% compared to 2019 budget | Decide the potential of CORYS and grow or abandon | Cashflow/payment terms | Add 1 more HxGN content customer of 5 MDKK | positive mindset towards profitability across the organisation | Establish a product support group | Improve the employee engagement by at least 4 points compared to 2019 | Develop and launch 1 new products / data services with annual turnover >5 MDKK and profit >20% | Implement single window platform for authoritative reporting and project status monitoring |  | NPS>40 | >90% customer FTR | 100% bids with Risk log and BoE | EBIT > 20% | Cash flow overdue < 3% turnover | Average cost of projects < 100% of project budget | EES>75 | Min 5 * 5Star leaders | Aerial Survey Units 100% utilized | Orderbacklog 6 months with next 2 months 100% | ROIC > 40% | Calendar | [11 empty] | SIMU | SRJ | BATX | ANDZ | OSK | MENE | STD | MJSK | CHEE | PBSO
|  | 2 | [7 empty] | 1 |  | 2 | 2 | 1 |  | 2 |  |  |  | 2 |  | Achieve a Turnover of 300 Mio MDKK (50 MUSD) | D | D | Q | C | C | C | P | P | G | G | G | [12 empty] | ½
|  |  | 2 | 2 | 2 | 2 |  |  |  |  | 1 | [5 empty] | 1 |  |  |  | 1 | Cost leadership by improving processing cost by factor 10 | D: KPI Q = Quality D = Delivery C = Cost P = People G = Growth
|  |  | 2 | 2 | 2 | 2 |  | 2 |  |  | 2 |  |  |  | 2 |  | 2 |  |  | 2 |  | Achieve an EBIT margin of > 20%
[10 empty] | 1 | 2 | [7 empty] | 1 |  | 2 | CMMi Lv 2
[9 empty] | 1 | 2 |  |  | 2 |  |  | 2 |  | 2 |  | 2 |  | 75% of all revenue from Content
[6 empty] | 2 | 3 |  | 1 |  | 2 | [10 empty] | Industry leading data acquisition cost/km2
|  | 1 | [6 empty] | 2 | 1 |  |  | 2 |  |  | 2 |  | 2 |  | 2 |  | Largest content provider in Europe (content: data, services, analytics)
[9 empty] | 1 | 1 |  | 2 | 2 |  |  |  |  | 2 |  |  |  | Go-To Partner and advisor for NMAs in Europe re content and PPP
|  |  | 2 | [10 empty] | 2 | [7 empty] | Revenue 15% Transport
[10 empty] | 2 | 1 | [5 empty] | 1 | 1 | 2 |  | 2 | Returning customers > 60%; NPS>50
[9 empty] | 1 | 2 | [7 empty] | 2 | 2 |  | 2 | "Easy to work with" towards the customer
[9 empty] | 2 | [6 empty] | 1 | 1 |  | 2 |  | 1 | Top 5 places to work in India, Europe all relevant rankings
[7 empty] | 1 |  |  | 2 | [6 empty] | 1 |  | 2 |  | 2 | Agile organization that supports the Growth (crowdsourcing, home-office)
101.
Annual improvement priorities
How much
Targets to improve
Business Unit
Breakthrough objectives
2020 - 2022
Business Unit
Annual objectives

## First-Level Template
Organization
Created by
Date
[9 empty] | Calendar for ACTIONPLANS | [11 empty] | RACI for ACTIONPLANS
Correlation |  |  |  | Annual Priority Actions | Correlation |  |  |  | Jan | Feb | Mar | Apr | Maj | Jun | Jul | Aug | Sep | Okt | Nov | Dec | Role 1 | Role 2 | Role 3 | PBSO | Statusv Date
|  |  |  | APA 1 | [16 empty] | A | C | C | R
|  |  |  | APA 2 | [16 empty] | I | C | C
|  |  |  | APA 3 | [16 empty] | I |  | A
AO 1 | AO 2 | AO 3 | AO 4 |  | KPI 1 | KPI 2 | KPI 3 | KPI 4 | Hoshin Kanri Matrix Company Name: Date: | [11 empty] | Role 1 | Role 2 | Role 3 | Role 4
KPI Types
BTO 1
BTO 1
BTO 3
BTO 4
| 1 | weak correlation
| 2 | strong correlation
Annual priority actions
How much
Targets to improve
Business Unit
Breakthrough objectives
20XX - 20XX
Business Unit
Annual objectives